## Project Data
id | name | start | end | type
0 | Residential Construction | 2024-05-27T08:00 | 2024-12-24T17:00 | FIXED_DURATION
1 | General Conditions | 2024-05-27T08:00 | 2024-06-24T17:00 | FIXED_DURATION
2 | Finalize plans and develop estimate with owner, architect | 2024-05-27T08:00 | 2024-06-21T17:00 | FIXED_UNITS
3 | Sign contract and notice to proceed | 2024-06-24T08:00 | 2024-06-24T17:00 | FIXED_UNITS
4 | Apply for Permits | 2024-06-24T17:00 | 2024-06-24T17:00 | FIXED_DURATION
5 | Secure foundation permit | 2024-06-24T17:00 | 2024-06-24T17:00 | FIXED_UNITS
6 | Secure framing permit | 2024-06-24T17:00 | 2024-06-24T17:00 | FIXED_UNITS
7 | Secure electrical permit | 2024-06-24T17:00 | 2024-06-24T17:00 | FIXED_UNITS
8 | Secure plumbing permit | 2024-06-24T17:00 | 2024-06-24T17:00 | FIXED_UNITS
9 | Secure HVAC permit | 2024-06-24T17:00 | 2024-06-24T17:00 | FIXED_UNITS
10 | Secure miscellaneous permits | 2024-06-24T17:00 | 2024-06-24T17:00 | FIXED_UNITS
11 | Site Work | 2024-06-25T08:00 | 2024-06-27T17:00 | FIXED_DURATION
12 | Clear and grub lot | 2024-06-25T08:00 | 2024-06-25T17:00 | FIXED_UNITS
13 | Install temporary power service | 2024-06-26T08:00 | 2024-06-26T17:00 | FIXED_UNITS
14 | Install underground utilities | 2024-06-27T08:00 | 2024-06-27T17:00 | FIXED_UNITS
15 | Foundation | 2024-06-28T08:00 | 2024-08-26T17:00 | FIXED_DURATION
16 | Excavate for foundations | 2024-06-28T08:00 | 2024-07-02T17:00 | FIXED_UNITS
17 | Form basement walls | 2024-07-03T08:00 | 2024-07-19T17:00 | FIXED_UNITS
18 | Place concrete for foundations & basement walls | 2024-07-22T08:00 | 2024-08-06T17:00 | FIXED_UNITS
19 | Cure basement walls for 7 days | 2024-08-07T08:00 | 2024-08-15T17:00 | FIXED_UNITS
20 | Strip basement wall forms | 2024-08-16T08:00 | 2024-08-19T17:00 | FIXED_UNITS
21 | Waterproof/insulate basement walls | 2024-08-20T08:00 | 2024-08-21T17:00 | FIXED_UNITS
22 | Perform foundation inspection | 2024-08-22T08:00 | 2024-08-22T17:00 | FIXED_UNITS
23 | Backfill foundation | 2024-08-23T08:00 | 2024-08-26T17:00 | FIXED_UNITS
24 | Framing | 2024-08-27T08:00 | 2024-09-25T17:00 | FIXED_DURATION
25 | Install 1st floor joists | 2024-08-27T08:00 | 2024-08-28T17:00 | FIXED_UNITS
26 | Lay 1st floor decking | 2024-08-29T08:00 | 2024-08-30T17:00 | FIXED_UNITS
27 | Frame 1st floor walls | 2024-09-02T08:00 | 2024-09-05T17:00 | FIXED_UNITS
28 | Frame 1st floor corners | 2024-09-06T08:00 | 2024-09-06T17:00 | FIXED_UNITS
29 | Install 2nd floor joists | 2024-09-09T08:00 | 2024-09-10T17:00 | FIXED_UNITS
30 | Frame 2nd floor decking | 2024-09-11T08:00 | 2024-09-12T17:00 | FIXED_UNITS
31 | Frame 2nd floor walls | 2024-09-13T08:00 | 2024-09-17T17:00 | FIXED_UNITS
32 | Frame 2nd floor corners | 2024-09-18T08:00 | 2024-09-19T17:00 | FIXED_UNITS
33 | Complete roof framing | 2024-09-20T08:00 | 2024-09-24T17:00 | FIXED_UNITS
34 | Conduct framing inspection | 2024-09-25T08:00 | 2024-09-25T17:00 | FIXED_UNITS
35 | Dry In | 2024-09-25T08:00 | 2024-10-24T17:00 | FIXED_DURATION
36 | Install 1st floor sheathing | 2024-09-26T08:00 | 2024-09-30T17:00 | FIXED_UNITS
37 | Install 2nd floor sheathing | 2024-10-01T08:00 | 2024-10-03T17:00 | FIXED_UNITS
38 | Install roof decking | 2024-09-25T08:00 | 2024-09-27T17:00 | FIXED_UNITS
39 | Install felt, flashing and shingles | 2024-10-11T08:00 | 2024-10-15T17:00 | FIXED_UNITS
40 | Hang 1st floor exterior doors | 2024-10-16T08:00 | 2024-10-16T17:00 | FIXED_UNITS
41 | Install 1st floor windows | 2024-10-17T08:00 | 2024-10-21T17:00 | FIXED_UNITS
42 | Install 2nd floor windows | 2024-10-22T08:00 | 2024-10-24T17:00 | FIXED_UNITS
43 | Exterior Finishes | 2024-10-25T08:00 | 2024-11-20T17:00 | FIXED_DURATION
44 | Complete exterior brick | 2024-10-25T08:00 | 2024-11-15T17:00 | FIXED_UNITS
45 | Complete exterior siding | 2024-11-18T08:00 | 2024-11-20T17:00 | FIXED_UNITS
46 | Utility Rough-B97Ins and Complete Concrete | 2024-09-30T08:00 | 2024-10-28T17:00 | FIXED_DURATION
47 | Rough-in plumbing | 2024-10-04T08:00 | 2024-10-10T17:00 | FIXED_UNITS
48 | Conduct rough-in plumbing inspection | 2024-10-11T08:00 | 2024-10-11T17:00 | FIXED_UNITS
49 | Place concrete for basement floor | 2024-10-14T08:00 | 2024-10-28T17:00 | FIXED_UNITS
50 | Rough-in electrical | 2024-10-04T08:00 | 2024-10-10T17:00 | FIXED_UNITS
51 | Conduct rough-in electrical inspection | 2024-10-11T08:00 | 2024-10-11T17:00 | FIXED_UNITS
52 | Rough-in HVAC | 2024-10-14T08:00 | 2024-10-16T17:00 | FIXED_UNITS
53 | Conduct rough-in HVAC inspection | 2024-10-17T08:00 | 2024-10-17T17:00 | FIXED_UNITS
54 | Rough-in communication - phone, cable, computer, alarm | 2024-09-30T08:00 | 2024-10-01T17:00 | FIXED_UNITS
55 | Interior Finishes | 2024-10-25T08:00 | 2024-12-05T17:00 | FIXED_DURATION
56 | Insulation | 2024-10-25T08:00 | 2024-11-08T17:00 | FIXED_DURATION
57 | Place wall insulation - 1st floor | 2024-10-25T08:00 | 2024-10-25T17:00 | FIXED_UNITS
58 | Place wall insulation - 2nd floor | 2024-10-28T08:00 | 2024-10-28T17:00 | FIXED_UNITS
59 | Place ceiling insulation - 2nd floor | 2024-11-07T08:00 | 2024-11-07T17:00 | FIXED_UNITS
60 | Conduct insulation inspection | 2024-11-08T08:00 | 2024-11-08T17:00 | FIXED_UNITS
61 | Drywall | 2024-10-28T08:00 | 2024-11-07T17:00 | FIXED_DURATION
62 | Install drywall - 1st floor walls | 2024-10-28T08:00 | 2024-10-29T17:00 | FIXED_UNITS
63 | Install drywall - 1st floor overhead | 2024-10-30T08:00 | 2024-10-31T17:00 | FIXED_UNITS
64 | Install drywall 2nd floor walls | 2024-11-01T08:00 | 2024-11-04T17:00 | FIXED_UNITS
65 | Install drywall 2nd floor overhead | 2024-11-05T08:00 | 2024-11-06T17:00 | FIXED_UNITS
66 | Tape and float 1st floor drywall | 2024-11-01T08:00 | 2024-11-01T17:00 | FIXED_UNITS
67 | Tape and float 2nd floor drywall | 2024-11-07T08:00 | 2024-11-07T17:00 | FIXED_UNITS
68 | Paint and Wallpaper | 2024-11-04T08:00 | 2024-11-26T17:00 | FIXED_DURATION
69 | Texture all except entry and kitchen - 1st floor | 2024-11-04T08:00 | 2024-11-04T17:00 | FIXED_UNITS
70 | Paint all except entry and kitchen - 1st floor | 2024-11-05T08:00 | 2024-11-05T17:00 | FIXED_UNITS
71 | Hang wallpaper entry and kitchen - 1st floor | 2024-11-06T08:00 | 2024-11-06T17:00 | FIXED_UNITS
72 | Texture all - 2nd floor | 2024-11-05T08:00 | 2024-11-05T17:00 | FIXED_UNITS
73 | Paint all - 2nd floor | 2024-11-06T08:00 | 2024-11-06T17:00 | FIXED_UNITS
74 | Paint exterior siding & trim work | 2024-11-21T08:00 | 2024-11-26T17:00 | FIXED_UNITS
75 | Cabinets | 2024-11-07T08:00 | 2024-11-14T17:00 | FIXED_DURATION
76 | Install 1st floor - kitchen cabinets | 2024-11-07T08:00 | 2024-11-08T17:00 | FIXED_UNITS
77 | Install 1st floor - master bath and guest cabinets | 2024-11-11T08:00 | 2024-11-11T17:00 | FIXED_UNITS
78 | Install 2nd floor - hall bath and private bath cabinets | 2024-11-12T08:00 | 2024-11-12T17:00 | FIXED_UNITS
79 | Install chair rails, crown moldings, trim | 2024-11-13T08:00 | 2024-11-14T17:00 | FIXED_UNITS
80 | Finish Plumbing | 2024-11-11T08:00 | 2024-11-18T17:00 | FIXED_DURATION
81 | Complete 1st floor - kitchen plumbing | 2024-11-11T08:00 | 2024-11-11T17:00 | FIXED_UNITS
82 | Complete 1st floor - master bath and guest plumbing | 2024-11-12T08:00 | 2024-11-13T17:00 | FIXED_UNITS
83 | Complete 2nd floor - hall bath and private bath plumbing | 2024-11-14T08:00 | 2024-11-15T17:00 | FIXED_UNITS
84 | Conduct finish plumbing inspection | 2024-11-18T08:00 | 2024-11-18T17:00 | FIXED_UNITS
85 | Finish Electrical | 2024-11-18T08:00 | 2024-11-20T17:00 | FIXED_DURATION
86 | Complete 1st floor circuits to service panel | 2024-11-18T08:00 | 2024-11-18T17:00 | FIXED_UNITS
87 | Complete 2nd floor circuits to service panel | 2024-11-19T08:00 | 2024-11-19T17:00 | FIXED_UNITS
88 | Conduct finish electrical inspection | 2024-11-20T08:00 | 2024-11-20T17:00 | FIXED_UNITS
89 | Complete communications wiring - phone, cable, computer, alarm | 2024-11-19T08:00 | 2024-11-20T17:00 | FIXED_UNITS
90 | Finish HVAC | 2024-11-21T08:00 | 2024-11-25T17:00 | FIXED_DURATION
91 | Complete 1st floor - zone 1 HVAC | 2024-11-21T08:00 | 2024-11-21T17:00 | FIXED_UNITS
92 | Complete 2nd floor - zone 2 HVAC | 2024-11-22T08:00 | 2024-11-22T17:00 | FIXED_UNITS
93 | Conduct HVAC inspection | 2024-11-25T08:00 | 2024-11-25T17:00 | FIXED_UNITS
94 | Carpet, Tile and Appliances | 2024-11-26T08:00 | 2024-12-05T17:00 | FIXED_DURATION
95 | Tile entry, kitchen and baths | 2024-11-26T08:00 | 2024-11-28T17:00 | FIXED_UNITS
96 | Carpet 1st floor | 2024-11-29T08:00 | 2024-12-02T17:00 | FIXED_UNITS
97 | Carpet 2nd floor | 2024-12-03T08:00 | 2024-12-04T17:00 | FIXED_UNITS
98 | Install appliances | 2024-12-05T08:00 | 2024-12-05T17:00 | FIXED_UNITS
99 | Landscaping and Grounds Work | 2024-11-27T08:00 | 2024-12-12T17:00 | FIXED_DURATION
100 | Pour concrete driveway and sidewalks | 2024-11-27T08:00 | 2024-11-28T17:00 | FIXED_UNITS
101 | Install backyard fence | 2024-12-06T08:00 | 2024-12-09T17:00 | FIXED_UNITS
102 | Sod and complete plantings - front yard | 2024-12-10T08:00 | 2024-12-11T17:00 | FIXED_UNITS
103 | Sod and complete plantings - backyard | 2024-12-12T08:00 | 2024-12-12T17:00 | FIXED_UNITS
104 | Final Acceptance | 2024-12-13T08:00 | 2024-12-24T17:00 | FIXED_DURATION
105 | Complete final inspection for certificate of occupancy | 2024-12-13T08:00 | 2024-12-13T17:00 | FIXED_UNITS
106 | Cleanup for occupancy | 2024-12-16T08:00 | 2024-12-16T17:00 | FIXED_UNITS
107 | Perform final walk-through inspection | 2024-12-17T08:00 | 2024-12-17T17:00 | FIXED_UNITS
108 | Complete punch list items | 2024-12-18T08:00 | 2024-12-24T17:00 | FIXED_UNITS